Monthly Financial Report

April 2026

# Participant and Partner Services Center (PPSC)

| Presented by: NORC at the University of Chicago |  | Presented to: All of Us Research Program National Institutes of Health (NIH) |
| --- | --- | --- |

## April 2026 Monthly Financial Report

This financial report summarizes the expenditures invoiced for the PPSC for April 2026. A listing of incurred and forecasted monthly costs by milestone is presented in the attached Financial Reporting Templates (provided by Attachment 5 of the Other Transactions Agreement). Attachment 5 for Year 2 milestones reflects a negative balance; this has not yet accounted for the impact of anticipated changes to our actual NICRA rates for 2025 which will counteract this.  Both the invoice and Attachment 5 for Year 3 milestones also include the cost share credit of $300,000, which was applied to the fee row of Milestone 53. Given that costs incurred to Milestone 53 generated $3,690 of fee in April 2026, the credit appears as a -$296,310 fee for Milestone 53 this month.

### Costs Incurred

All NORC labor details, including a list of personnel, hourly rates, and hours, can be found in the monthly invoices included with this submission. An additional breakdown of staff hours by labor category is attached per NIH request. NORC’s April Financial Report includes IBM’s February and March 2026 invoices at a total cost of $3,111,511, Westat’s February and March 2026 invoices at a total cost of $63,372, River Valley Health’s November 2025 and February 2026 invoices at a total cost of $26,732, and Palladian’s January 2026 invoice at a cost of $76,328. Cost details from IBM, Westat, River Valley Health, and Palladian are represented in their detailed invoices, included as attachments to NORC’s April invoices. The April invoices include corrections (i.e., negative charges to 9877.25 and positive charges to 9877.26) for costs incurred during the no cost extension by outside staff and Support Center staff. Additionally, a processing error that occurred when NORC attempted to correct February charges to Milestone 54 that were attributable to Milestone 55 was corrected on the April invoice; these appear as negative charges to Milestone 54 and positive charges to Milestone 55. Adjustments to accurately apply the salary cap to affected project staff members were issued on NORC’s April invoice. The NORC team incurred a charge of $650,000 within Milestone 25 to seed the project Tango Card account for digital participant Reassessment compensation. Also included are other direct costs in Table 3 and detailed travel costs for trips that were billed in April 2026 in Table 5.

Table 1 shows the current award budget overview for the PPSC Award for 2026. Further details regarding the 2025 award and 2025 milestones that continue into 2026 are included in Attachment 5 and NORC’s April invoice. NORC has received approval from NIH for rebudgeting across milestones as of April 8, 2026; these rebudgeted amounts are reflected in NORC’s April Financial Report and corresponding Attachment 5.

Table 1. PPSC Summary of Financial Status: April 2026 (01/01/2026 – 4/25/2026)

|  | Current Month Expenditure (3/28/2026 – 4/25/2026) | Cumulative Expenditure (as of 4/26/2026) | Planned Future Expenditures | Total Planned Expenditure | Award Balance |
| --- | --- | --- | --- | --- | --- |
| Budget | $4,099,161 | $18,578,561 | $15,129,404 | $33,707,965 | $33,707,478 |
| Percent | - 12.2% | - 55.1% | - 44.9% | - 100.0% | - 100.0% |

Other Direct Costs

Table 3 outlines other direct costs included in the April 2026 invoice.

Table 3. Other Direct Costs

| Vendor | Purpose | Cost |
| --- | --- | --- |
| Jellyfish | Google Analytics licensing costs | $6,525 |
| EasyPost | API tracking software | $100 |
| Carahsoft | Salesforce licensing costs | $60,038 |
| Amazon Web Services | Amazon Web Services costs | $16,715 |
| Panelists | WD-FAB CEP panelist honoraria | $100 |
| NORC IRB | IRB review fees | $350 |
| ElevenLabs | Voiceover software licenses | $152 |

Outside Staff

NORC regularly uses contractors from staffing agencies to serve as staff extenders, particularly in IT, where the staffing levels can fluctuate. These contractors are different than subcontractors with a defined scope of work. Their rates are comparable to the loaded rates for NORC staff in similar roles. Outside staff costs for the month are described in Table 4. The labor costs for outside staff are attributed to the month when the invoice was processed, rather than the month when the labor cost was incurred.

Table 4. Summary of Outside Staff Costs

| Name | Job Title | Hours | Contracted Hourly Rate | Total |
| --- | --- | --- | --- | --- |
| Savitha Narayan | Project Manager, Integrations Specialist | 40 | $140.00 | $5,600.00 |
| Patrick O’Brien | Senior Project Manager, Security Specialist | 33 | $142.00 | $4,686.00 |
| Daniel Tuveson | Survey Programmer | 48.75 | $95.17 | $4,639.52 |
| Ryan Hollm | Communications/ Methods Consultant | 149.5 | $130.00 | $19,435.00 |
| Michael Travor | Knowledge Article Manager | 336 | $90.00 | $30,240.00 |
| Total Outside Staff Costs |  |  |  | $64,600.52 |

Travel Costs

Table 5 outlines travel expenses incurred by NORC staff for PPSC-related meetings.

Table 5. Summary of April Travel Costs

| Travel Purpose | Location | Traveler | Dates of Travel | Length of Stay | Total Expenses (Hotel, Airfare/Transportation, Meals & Incidentals) |
| --- | --- | --- | --- | --- | --- |
| Transition Meeting | Bethesda, MD | Lydia Luy-Tan | 1/27/2026-1/29/2026 | 2 nights | $551.80 |
| Total Travel Expenses |  |  |  |  | $551.80 |