## April 2026
[15 empty] | Actual | Forecast
Award Number | OT2OD036464 |  |  | Cells that require montly updates/reporting
Award Dollars for Award Year 2026 | 33707478.4095 |  |  | Cells that require initial setup
Reporting Month | Percent Spent | Award $ | [12 empty] | Totals Summary
|  |  | Actual | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Total Actual | Total Forecast | Total Estimate Spending | Estimated Balance
|  |  | January 2026 | February 2026 | March 2026 | April 2026 | May 2026 | June 2026 | July 2026 | August 2026 | September 2026 | October 2026 | November 2026 | December 2026
April | 55.12% | 33707478.4095 | 0 | 11787301.554 | 2692098.1945 | 4099160.976 | 2629214.6742 | 2384619.0209 | 2534941.6179 | 2574573.8686 | 3028015.837 | 612057.5503 | 594751.7043 | 771229.5816 | 18578560.7245 | 15129403.8549 | 33707964.5794 | -486.1699
Milestone 44- Directorate
Direct Costs - Milestone 44
Labor | 29.8% | 92122 | 0 | 27454.42 | 21102.59 | 11151.79 | 11962.8011 | 11962.8011 | 5534.5132 | 5534.5132 | 5534.5132 | 0 | 0 | 0 | 59708.8 | 40529.1419 | 100237.9419 | -8115.9419
Travel | #DIV/0! | 0 | 0 | 3451.77 | 1058.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4510.06 | 0 | 4510.06 | -4510.06
ODC | 0.7703% | 211119 | 0 | 1626.15 | 27281.15 | 113168.59 | 21177.2 | 10877.2 | 10596 | 10596 | 16452.2401 | 0 | 0 | 0 | 142075.89 | 69698.6401 | 211774.5301 | -655.5301
Subtotal Direct costs Milestone 44 |  | 303241 | 0 | 32532.34 | 49442.03 | 124320.38 | 33140.0011 | 22840.0011 | 16130.5132 | 16130.5132 | 21986.7533 | 0 | 0 | 0 | 206294.75 | 110227.782 | 316522.532 | -13281.532
Indirect Costs - Milestone 44 |  | 80397.75 | 0 | 22790.36 | 17310.09 | 9806.12 | 9697.5387 | 9630.0387 | 4498.0637 | 4498.0637 | 4536.4419 | 0 | 0 | 0 | 49906.57 | 32860.1467 | 82766.7167 | -2368.9667
Fee costs Milestone 44 |  | 19182.9375 | 0 | 2766.135 | -1551.04 | 6706.325 | 2141.877 | 1623.502 | 1031.4288 | 1031.4288 | 1326.1598 | 0 | 0 | 0 | 7921.42 | 7154.3964 | 15075.8164 | 4107.1211
Total Milestone 44 | 14.42% | 402821.6875 | 0 | 58088.835 | 65201.08 | 140832.825 | 44979.4168 | 34093.5418 | 21660.0057 | 21660.0057 | 27849.355 | 0 | 0 | 0 | 264122.74 | 150242.3252 | 414365.0652 | -11543.3777
Milestone 45- Product Implementation
Direct Costs - Milestone 45
Labor | 30.44% | 40321 | 0 | 12273.01 | 14057.41 | 3326.92 | 1191.0732 | 2641.7128 | 2641.7128 | 0 | 0 | 0 | 0 | 0 | 29657.34 | 6474.4988 | 36131.8388 | 4189.1612
Travel | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC | 0.3719% | 2135256 | 0 | 7940.25 | 193074.22 | 490987.01 | 236129.4 | 236233 | 280187.0861 | 217424.3789 | 472110.8 | 0 | 0 | 0 | 692001.48 | 1442084.665 | 2134086.145 | 1169.855
Subtotal Direct costs Milestone 45 |  | 2175577 | 0 | 20213.26 | 207131.63 | 494313.93 | 237320.4732 | 238874.7128 | 282828.7989 | 217424.3789 | 472110.8 | 0 | 0 | 0 | 721658.82 | 1448559.1638 | 2170217.9838 | 5359.0162
Indirect Costs - Milestone 45 |  | 48724 | 0 | 11469.96 | 12562.12 | 5898.29 | 2502.7762 | 3669.9155 | 3957.9642 | 1424.8685 | 3093.93 | 0 | 0 | 0 | 29930.37 | 14649.4544 | 44579.8244 | 4144.1756
Fee costs Milestone 45 |  | 111215.05 | 0 | 1584.161 | 10984.6875 | 25010.611 | 11991.1625 | 12127.2314 | 14339.3382 | 23759.3553 | 23760.2365 | 0 | 0 | 0 | 37579.4595 | 85977.3238 | 123556.7833 | -12341.7333
Total Milestone 45 | 1.424% | 2335517.05 | 0 | 33267.381 | 230678.4375 | 525222.831 | 251814.4119 | 254671.8597 | 301126.1012 | 242608.6027 | 498964.9665 | 0 | 0 | 0 | 789168.6495 | 1549185.942 | 2338354.5915 | -2838.5415
Milestone 46- Website Maintenance
Direct Costs - Milestone 46
Labor | 280.2% | 5251 |  | 14710.79 | 281.37 | 0 | 131.1206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14992.16 | 131.1206 | 15123.2806 | -9872.2806
Travel | #DIV/0! | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC | 1.563% | 1016309 |  | 15883.6 | 102181.51 | 244079.29 | 110657.21 | 110649.81 | 118946.4909 | 118946.4909 | 176588.0925 | 6720.75 | 0 | 0 | 362144.4 | 642508.8443 | 1004653.2443 | 11655.7557
Subtotal Direct costs Milestone 46 |  | 1021560 | 0 | 30594.39 | 102462.88 | 244079.29 | 110788.3306 | 110649.81 | 118946.4909 | 118946.4909 | 176588.0925 | 6720.75 | 0 | 0 | 377136.56 | 642639.9649 | 1019776.5249 | 1783.4751
Indirect Costs - Milestone 46 |  | 26091 |  | 15173.29 | 2322.12 | 3024.92 | 830.1858 | 725.1322 | 779.5037 | 779.5037 | 1157.2521 | 44.0438 | 0 | 0 | 20520.33 | 4315.6213 | 24835.9513 | 1255.0487
Fee costs Milestone 46 |  | 52382.55 | 0 | 2288.384 | 5239.25 | 12355.2105 | 5580.9258 | 5568.7471 | 5986.2997 | 5986.2997 | 8887.2672 | 338.2397 | 0 | 0 | 19882.8445 | 32347.7793 | 52230.6238 | 151.9262
Total Milestone 46 | 4.369% | 1100033.55 | 0 | 48056.064 | 110024.25 | 259459.4205 | 117199.4423 | 116943.6894 | 125712.2943 | 125712.2943 | 186632.6118 | 7103.0334 | 0 | 0 | 417539.7345 | 679303.3655 | 1096843.1 | 3190.45
Milestone 47- Communications Delivery
Direct Costs - Milestone 47
Labor | 247.1% | 5251 |  | 12975.64 | 9799.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22775.5 | 0 | 22775.5 | -17524.5
Travel | #DIV/0! | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC | 0.1518% | 1583575 |  | 2404.4 | 179961 | 315548.64 | 175919.88 | 175919.88 | 175919.88 | 209723.8826 | 351839.8115 | 0 | 0 | 0 | 497914.04 | 1089323.3341 | 1587237.3741 | -3662.3741
Subtotal Direct costs Milestone 47 |  | 1588826 | 0 | 15380.04 | 189760.86 | 315548.64 | 175919.88 | 175919.88 | 175919.88 | 209723.8826 | 351839.8115 | 0 | 0 | 0 | 520689.54 | 1089323.3341 | 1610012.8741 | -21186.8741
Indirect Costs - Milestone 47 |  | 13736 |  | 10772.27 | 9246 | 2067.92 | 1152.873 | 1152.873 | 1152.873 | 1374.4041 | 2305.7463 | 0 | 0 | 0 | 22086.19 | 7138.7694 | 29224.9594 | -15488.9594
Fee costs Milestone 47 |  | 80128.1 | 0 | 1307.6155 | 9950.343 | 15880.828 | 8853.6377 | 8853.6377 | 8853.6377 | 10554.9143 | 17707.2779 | 0 | 0 | 0 | 27138.7865 | 54823.1052 | 81961.8917 | -1833.7917
Total Milestone 47 | 1.632% | 1682690.1 | 0 | 27459.9255 | 208957.203 | 333497.388 | 185926.3907 | 185926.3907 | 185926.3907 | 221653.201 | 371852.8357 | 0 | 0 | 0 | 569914.5165 | 1151285.2087 | 1721199.7252 | -38509.6252
Milestone 48- Data Quality & Platform analytics
Direct Costs - Milestone 48
Labor | 19.84% | 209328.21 |  | 41525.74 | 28522.26 | 23388.64 | 33703.108 | 29568.4927 | 25553.053 | 17413.1526 | 3839.876 | 1048.9648 | 0 | 0 | 93436.64 | 111126.6472 | 204563.2872 | 4764.9228
Travel | #DIV/0! | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC | 1.451% | 498039 |  | 7228.85 | 32835.15 | 165838.92 | 56230.17 | 55845.37 | 78898.692 | 54216.9615 | 53284.5615 | 59.2 | 0 | 0 | 205902.92 | 298534.955 | 504437.875 | -6398.875
Subtotal Direct costs Milestone 48 |  | 707367.21 | 0 | 48754.59 | 61357.41 | 189227.56 | 89933.278 | 85413.8627 | 104451.745 | 71630.1141 | 57124.4375 | 1108.1648 | 0 | 0 | 299339.56 | 409661.6022 | 709001.1622 | -1633.9522
Indirect Costs - Milestone 48 |  | 183014.92 |  | 33887.76 | 22376.27 | 19436.12 | 27463.9139 | 24117.1898 | 21053.598 | 14337.7509 | 3425.4323 | 840.4287 | 0 | 0 | 75700.15 | 91238.3137 | 166938.4637 | 16076.4563
Fee costs Milestone 48 |  | 44519.1065 | 0 | 4132.1175 | 3666.1 | 10433.184 | 5869.8596 | 5476.5526 | 6275.2671 | 4298.3933 | 3027.4935 | 97.4297 | 0 | 0 | 18231.4015 | 25044.9958 | 43276.3973 | 1242.7092
Total Milestone 48 | 9.282% | 934901.2365 | 0 | 86774.4675 | 87399.78 | 219096.864 | 123267.0516 | 115007.6051 | 131780.6101 | 90266.2583 | 63577.3633 | 2046.0232 | 0 | 0 | 393271.1115 | 525944.9116 | 919216.0231 | 15685.2134
Milestone 49- Tier 2&3 support
Direct Costs - Milestone 49
Labor | 33.46% | 311149.28 |  | 104097.32 | 37077 | 35894.48 | 37386.2972 | 30943.9901 | 26038.0207 | 14258.1402 | 14258.1402 | 10164.4069 | 5850.8897 | 2819.3768 | 177068.8 | 141719.2618 | 318788.0618 | -7638.7818
Travel | #DIV/0! |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC | 7.004% | 195136 |  | 13668.27 | 30258.91 | 50325.7 | 21906.6 | 21018.6 | 20286 | 17204.022 | 17204.022 | 1361.6 | 769.6 | 384.8 | 94252.88 | 100135.2441 | 194388.1241 | 747.8759
Subtotal Direct costs Milestone 49 |  | 506285.28 | 0 | 117765.59 | 67335.91 | 86220.18 | 59292.8972 | 51962.5901 | 46324.0207 | 31462.1622 | 31462.1622 | 11526.0069 | 6620.4897 | 3204.1768 | 271321.68 | 241854.5059 | 513176.1859 | -6890.9059
Indirect Costs - Milestone 49 |  | 273467.22 |  | 85156.13 | 30592.73 | 29814.73 | 30731.5803 | 25452.0212 | 21418.8293 | 11782.0456 | 11782.0456 | 8320.9948 | 4786.5865 | 2309.6586 | 145563.59 | 116583.7621 | 262147.3521 | 11319.8679
Fee costs Milestone 49 |  | 38987.625 | 0 | 10146.086 | 4896.432 | 5801.7455 | 4501.2239 | 3870.7306 | 3387.1425 | 2162.2104 | 2162.2104 | 992.3501 | 570.3538 | 275.6918 | 20844.2635 | 17921.9134 | 38766.1769 | 221.4481
Total Milestone 49 | 26.02% | 818740.125 | 0 | 213067.806 | 102825.072 | 121836.6555 | 94525.7013 | 81285.3419 | 71129.9926 | 45406.4182 | 45406.4182 | 20839.3518 | 11977.43 | 5789.5272 | 437729.5335 | 376360.1813 | 814089.7148 | 4650.4102
Milestone 50- Development + Operations & Maintenance
Direct Costs - Milestone 50
Labor | 35.25% | 216764 |  | 76402.77 | 47679.17 | 30408.82 | 22004.5799 | 13560.3088 | 10382.1656 | 6286.7862 | 1664.7025 | 171.9231 | 171.9231 | 154.7307 | 154490.76 | 54397.1199 | 208887.8799 | 7876.1201
Travel | #DIV/0! | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC | 0.827% | 6626937 |  | 54801.58 | 591729.88 | 1558955.97 | 725063.38 | 724471.38 | 869742.7418 | 1024997.9215 | 1024672.3215 | 9639.8 | 9639.8 | 8675.82 | 2205487.43 | 4396903.1649 | 6602390.5949 | 24546.4051
Subtotal Direct costs Milestone 50 |  | 6843701 | 0 | 131204.35 | 639409.05 | 1589364.79 | 747067.9599 | 738031.6888 | 880124.9074 | 1031284.7078 | 1026337.0241 | 9811.7231 | 9811.7231 | 8830.5507 | 2359978.19 | 4451300.2848 | 6811278.4748 | 32422.5252
Indirect Costs - Milestone 50 |  | 261611 |  | 72573.96 | 46571.12 | 38412.64 | 24541.0217 | 17749.514 | 16143.841 | 13873.8891 | 10156.1161 | 2304.5163 | 2304.5163 | 2074.0647 | 157557.72 | 89147.4794 | 246705.1994 | 14905.8006
Fee costs Milestone 50 |  | 355265.6 | 0 | 10188.9155 | 33818.77 | 81388.8715 | 38580.4491 | 37789.0601 | 44813.4374 | 52257.9298 | 51824.657 | 605.812 | 605.812 | 605.812 | 125396.557 | 227082.9694 | 352479.5264 | 2786.0736
Total Milestone 50 | 2.868% | 7460577.6 | 0 | 213967.2255 | 719798.94 | 1709166.3015 | 810189.4307 | 793570.263 | 941082.1859 | 1097416.5267 | 1088317.7972 | 12722.0514 | 12722.0514 | 11510.4274 | 2642932.467 | 4767530.7335 | 7410463.2005 | 50114.3995
Milestone 51- Data. Process amd protocol automation
Direct Costs - Milestone 51
Labor | 3.08% | 77316 |  | 2381.32 | 3204.91 | 5850.18 | 15190.1149 | 15190.1149 | 13999.0417 | 13284.3978 | 0 | 0 | 0 | 0 | 11436.41 | 57663.6693 | 69100.0793 | 8215.9207
Travel | #DIV/0! |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC | 0.03177% | 465865 |  | 148 | 104456.44 | 249331.57 | 22462.8353 | 22462.8353 | 22388.8353 | 22344.4353 | 21574.8353 | 0 | 0 | 0 | 353936.01 | 111233.7763 | 465169.7863 | 695.2137
Subtotal Direct costs Milestone 51 |  | 543181 | 0 | 2529.32 | 107661.35 | 255181.75 | 37652.9502 | 37652.9502 | 36387.877 | 35628.833 | 21574.8353 | 0 | 0 | 0 | 365372.42 | 168897.4456 | 534269.8656 | 8911.1344
Indirect Costs - Milestone 51 |  | 69198 |  | 1910.97 | 3253.65 | 6321.21 | 12318.5941 | 12318.5941 | 11362.7829 | 10789.2961 | 141.3885 | 0 | 0 | 0 | 11485.83 | 46930.6557 | 58416.4857 | 10781.5143
Fee costs Milestone 51 |  | 30618.95 | 0 | 222.0145 | 5545.75 | 13075.148 | 2498.5772 | 2498.5772 | 2387.533 | 2320.9065 | 1085.8112 | 0 | 0 | 0 | 18842.9125 | 10791.4051 | 29634.3176 | 984.6324
Total Milestone 51 | 0.7251% | 642997.95 | 0 | 4662.3045 | 116460.75 | 274578.108 | 52470.1215 | 52470.1215 | 50138.1928 | 48739.0356 | 22802.0349 | 0 | 0 | 0 | 395701.1625 | 226619.5063 | 622320.6688 | 20677.2812
Milestone 52- Security
Direct Costs - Milestone 52
Labor | 33.8% | 106061.27 |  | 35853.88 | 19297.8 | 12969.06 | 10004.4298 | 10004.4298 | 10004.4298 | 10004.4298 | 5526.6973 | 2896.4325 | 2896.4325 | 2896.4325 | 68120.74 | 54233.7137 | 122354.4537 | -16293.1837
Travel | #DIV/0! |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC | 1.751% | 260251 |  | 4557.9 | 6952.1 | 56466.2 | 18766.36 | 18766.36 | 18766.36 | 20682.439 | 107906.839 | 207.2 | 207.2 | 207.2 | 67976.2 | 185509.958 | 253486.158 | 6764.842
Subtotal Direct costs Milestone 52 |  | 366312.27 | 0 | 40411.78 | 26249.9 | 69435.26 | 28770.7898 | 28770.7898 | 28770.7898 | 30686.8688 | 113433.5363 | 3103.6325 | 3103.6325 | 3103.6325 | 136096.94 | 239743.6717 | 375840.6117 | -9528.3417
Indirect Costs - Milestone 52 |  | 116551.36 |  | 29296.32 | 16780.51 | 11817.82 | 8931.2239 | 8931.2239 | 8931.2239 | 8561.4992 | 5531.2971 | 2330.457 | 2330.457 | 2330.457 | 57894.65 | 47877.8388 | 105772.4888 | 10778.8712
Fee costs Milestone 52 |  | 24143.1815 | 0 | 3485.405 | 2151.5205 | 4062.654 | 2256.7501 | 2070.9254 | 1885.1007 | 1962.4184 | 5948.2417 | 527.5517 | 420.3642 | 271.7045 | 9699.5795 | 15343.0566 | 25042.6361 | -899.4546
Total Milestone 52 | 14.44% | 507006.8115 | 0 | 73193.505 | 45181.9305 | 85315.734 | 39958.7637 | 39772.939 | 39587.1143 | 41210.7863 | 124913.075 | 5961.6412 | 5854.4537 | 5705.7939 | 203691.1695 | 302964.5672 | 506655.7367 | 351.0748
Milestone 53- Licenses
Direct Costs - Milestone 53
Labor | #DIV/0! | 0 |  | 942091.11 | 0 | 133.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 942224.87 | 0 | 942224.87 | -942224.87
Travel | #DIV/0! |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC | 88.98% | 7313079 |  | 6506823.65 | 10550.6 | 60045.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6577419.78 | 0 | 6577419.78 | 735659.22
Subtotal Direct costs Milestone 53 |  | 7313079 | 0 | 7448914.76 | 10550.6 | 60179.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7519644.65 | 0 | 7519644.65 | -206565.65
Indirect Costs - Milestone 53 |  | 1462616 |  | 1676005.85 | 2373.89 | 13615.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1691995.46 | 0 | 1691995.46 | -229379.46
Fee costs Milestone 53 |  | 438784.75 | 0 | 456246.0305 | 646.2245 | -296310.2495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160582.0055 | 0 | 160582.0055 | 278202.7445
Total Milestone 53 | 104% | 9214479.75 | 0 | 9581166.6405 | 13570.7145 | -222515.2395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9372222.1155 | 0 | 9372222.1155 | -157742.3655
Milestone 54- Directorate and Management
Direct Costs - Milestone 54
Labor | 39.76% | 219465.26 |  | 87260.97 | 36131.27 | -24285.22 | 19310.5354 | 20064.9546 | 16673.2386 | 16673.2386 | 14271.6977 | 14271.6977 | 14271.6977 | 14271.6977 | 99107.02 | 129808.758 | 228915.778 | -9450.518
Travel | #DIV/0! | 0 |  | 1030.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030.92 | 0 | 1030.92 | -1030.92
ODC | 40.8% | 19869 |  | 8105.81 | 2569.65 | -3784.21 | 1213.6 | 1332 | 1147 | 1147 | 1117.4 | 1117.4 | 1117.4 | 1117.4 | 6891.25 | 9309.2 | 16200.45 | 3668.55
Subtotal Direct costs Milestone 54 |  | 239334.26 | 0 | 96397.7 | 38700.92 | -28069.43 | 20524.1354 | 21396.9546 | 17820.2386 | 17820.2386 | 15389.0977 | 15389.0977 | 15389.0977 | 15389.0977 | 107029.19 | 139117.958 | 246147.148 | -6812.888
Indirect Costs - Milestone 54 |  | 190080.1 |  | 70861.08 | 29067.65 | -20000.33 | 15499.4172 | 16120.9167 | 13404.9236 | 13404.9236 | 11504.6486 | 11504.6486 | 11504.6486 | 11504.6486 | 79928.4 | 104448.7757 | 184377.1757 | 5702.9243
Fee costs Milestone 54 |  | 21470.718 | 0 | 8362.939 | -1644.19 | -2403.488 | 1801.1776 | 1875.8936 | 1561.2581 | 1561.2581 | 1344.6873 | 1400.7243 | 1400.7243 | 1400.7243 | 4315.261 | 12346.4475 | 16661.7085 | 4809.0095
Total Milestone 54 | 38.95% | 450886.078 | 0 | 175621.719 | 66124.38 | -50473.248 | 37824.7303 | 39393.7649 | 32786.4203 | 32786.4203 | 28238.4336 | 28294.4706 | 28294.4706 | 28294.4706 | 191272.851 | 255913.1812 | 447186.0322 | 3699.0458
Milestone 55- Protocol Compliance
Direct Costs - Milestone 55
Labor | 11.95% | 283826.13 |  | 33916 | 50095.6 | 86979.52 | 28374.2795 | 28700.3454 | 15892.6803 | 12414.6436 | 12414.6436 | 8175.7864 | 8175.7864 | 8175.7864 | 170991.12 | 122323.9519 | 293315.0719 | -9488.9419
Travel | #DIV/0! | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC | 4.608% | 303363 |  | 13978.5 | 22214.2 | 28047.71 | 29343.6 | 29388 | 28426 | 27952.4 | 27952.4 | 27375.2 | 27375.2 | 34173.2 | 64240.41 | 231986 | 296226.41 | 7136.59
Subtotal Direct costs Milestone 55 |  | 587189.13 | 0 | 47894.5 | 72309.8 | 115027.23 | 57717.8795 | 58088.3454 | 44318.6803 | 40367.0436 | 40367.0436 | 35550.9864 | 35550.9864 | 42348.9864 | 235231.53 | 354309.9519 | 589541.4819 | -2352.3519
Indirect Costs - Milestone 55 |  | 286837.05 |  | 29887.94 | 44498.57 | 74894.09 | 27490.4294 | 27757.5224 | 17442.2284 | 14593.2365 | 14593.2365 | 11121.0276 | 11121.0276 | 11165.5776 | 149280.6 | 135284.2861 | 284564.8861 | 2272.1639
Fee costs Milestone 55 |  | 43701.309 | 0 | 3889.122 | 5840.4185 | 9496.066 | 4260.4154 | 4292.2934 | 3088.0454 | 2748.014 | 2748.014 | 2333.6007 | 2333.6007 | 2675.7282 | 19225.6065 | 24479.7119 | 43705.3184 | -4.0094
Total Milestone 55 | 8.899% | 917727.489 | 0 | 81671.562 | 122648.7885 | 199417.386 | 89468.7243 | 90138.1612 | 64848.9542 | 57708.2942 | 57708.2942 | 49005.6148 | 49005.6148 | 56190.2923 | 403737.7365 | 514073.9498 | 917811.6863 | -84.1973
Milestone 56- Partner and Participant Coordination
Direct Costs - Milestone 56
Labor | 23.74% | 289921 |  | 68816.69 | 38922.36 | 27364.54 | 30949.9181 | 25079.6906 | 25079.6906 | 23514.2966 | 15789.1839 | 13318.1723 | 12033.9932 | 10907.612 | 135103.59 | 156672.5573 | 291776.1473 | -1855.1473
Travel | #DIV/0! | 0 | 0 | 2833.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2833.27 | 0 | 2833.27 | -2833.27
ODC | 23.44% | 30244 | 0 | 7090.44 | 3796.2 | 2775 | 2967.4 | 2523.4 | 2523.4 | 2405 | 1561.4 | 1339.4 | 1221 | 1110 | 13661.64 | 15651 | 29312.64 | 931.36
Subtotal Direct costs Milestone 56 |  | 320165 | 0 | 78740.4 | 42718.56 | 30139.54 | 33917.3181 | 27603.0906 | 27603.0906 | 25919.2966 | 17350.5839 | 14657.5723 | 13254.9932 | 12017.612 | 151598.5 | 172323.5573 | 323922.0573 | -3757.0573
Indirect Costs - Milestone 56 |  | 251903 | 0 | 56494.82 | 31544.44 | 22201.32 | 25071.6754 | 20343.101 | 20343.101 | 19082.1479 | 12801.0865 | 10802.7439 | 9763.5286 | 8850.4021 | 110240.58 | 127057.7864 | 237298.3664 | 14604.6336
Fee costs Milestone 56 |  | 28603.4 | 0 | 6761.761 | 3713.15 | 2617.043 | 2949.4497 | 2397.3096 | 2397.3096 | 2250.0722 | 1507.5835 | 1273.0158 | 1150.9261 | 1043.4007 | 13091.954 | 14969.0672 | 28061.0212 | 542.3788
Total Milestone 56 | 23.64% | 600671.4 | 0 | 141996.981 | 77976.15 | 54957.903 | 61938.4432 | 50343.5012 | 50343.5012 | 47251.5167 | 31659.2539 | 26733.332 | 24169.4479 | 21911.4149 | 274931.034 | 314350.4109 | 589281.4449 | 11389.9551
Milestone 57- Data Governance and Delivery
Direct Costs - Milestone 57
Labor | 33.93% | 595940.98 |  | 202186.91 | 97299.93 | 77978.45 | 62576.4203 | 47437.7896 | 39618.2205 | 31144.2908 | 17841.1012 | 9776.106 | 9090.8193 | 10232.9639 | 377465.29 | 227717.7116 | 605183.0016 | -9242.0216
Travel | #DIV/0! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC | 36.01% | 45783.75 | 0 | 16486.46 | 7568.35 | 5877.45 | 4847 | 3885 | 3300.4 | 2715.8 | 1317.2 | 636.4 | 592 | 666 | 29932.26 | 17959.8 | 47892.06 | -2108.31
Subtotal Direct costs Milestone 57 |  | 641724.73 | 0 | 218673.37 | 104868.28 | 83855.9 | 67423.4203 | 51322.7896 | 42918.6205 | 33860.0908 | 19158.3012 | 10412.506 | 9682.8193 | 10898.9639 | 407397.55 | 245677.5116 | 653075.0616 | -11350.3316
Indirect Costs - Milestone 57 |  | 514514.71 | 0 | 163133.84 | 78423.87 | 62808.44 | 50432.0824 | 38278.8221 | 31981.5568 | 25168.3283 | 14364.0783 | 7851.6496 | 7301.311 | 8218.542 | 304366.15 | 183596.3706 | 487962.5206 | 26552.1894
Fee costs Milestone 57 |  | 57811.972 | 0 | 19090.3605 | 9164.6075 | 7333.217 | 5892.7751 | 4480.0806 | 3745.0089 | 2951.421 | 1676.119 | 913.2078 | 849.2065 | 955.8753 | 35588.185 | 21463.6941 | 57051.8791 | 760.0929
Total Milestone 57 | 33.02% | 1214051.412 | 0 | 400897.5705 | 192456.7575 | 153997.557 | 123748.2778 | 94081.6923 | 78645.1861 | 61979.8401 | 35198.4984 | 19177.3635 | 17833.3368 | 20073.3812 | 747351.885 | 450737.5762 | 1198089.4612 | 15961.9508
Milestone 58- TEP
Direct Costs - Milestone 58
Labor | 21.02% | 100135.97 |  | 21043.77 | 9797.23 | 7631.14 | 11020.7649 | 10084.8452 | 7631.14 | 7631.14 | 10084.8452 | 7631.14 | 10084.8452 | 10084.8452 | 38472.14 | 74253.5658 | 112725.7058 | -12589.7358
Travel | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC | 0.7364% | 301725 | 0 | 2221.85 | 953.86 | 728.16 | 132757 | 999 | 728.16 | 728.16 | 999 | 728.16 | 999 | 135999 | 3903.87 | 273937.48 | 277841.35 | 23883.65
Subtotal Direct costs Milestone 58 |  | 401860.97 | 0 | 23265.62 | 10751.09 | 8359.3 | 143777.7649 | 11083.8452 | 8359.3 | 8359.3 | 11083.8452 | 8359.3 | 11083.8452 | 146083.8452 | 42376.01 | 348191.0458 | 390567.0558 | 11293.9142
Indirect Costs - Milestone 58 |  | 145261.2 | 0 | 17092.96 | 7939.74 | 6180.99 | 38560.1981 | 8176.6755 | 6180.99 | 6180.99 | 8176.6755 | 6180.99 | 8176.6755 | 38551.6755 | 31213.69 | 120184.87 | 151398.56 | -6137.36
Fee costs Milestone 58 |  | 27356.1085 | 0 | 2017.929 | 934.5415 | 727.0145 | 9116.8981 | 963.026 | 963.026 | 963.026 | 963.026 | 963.026 | 963.026 | 9231.776 | 3679.485 | 24126.8304 | 27806.3154 | -450.2069
Total Milestone 58 | 7.377% | 574478.2785 | 0 | 42376.509 | 19625.3715 | 15267.3045 | 191454.8611 | 20223.5467 | 15503.316 | 15503.316 | 20223.5467 | 15503.316 | 20223.5467 | 193867.2967 | 77269.185 | 492502.7461 | 569771.9311 | 4706.3474
Milestone 59- Support Center
Direct Costs - Milestone 59
Labor | 12.91% | 2449996.01 |  | 316402.38 | 266967.1 | 127769.13 | 203215.5844 | 213911.1414 | 213911.1414 | 213911.1414 | 213911.1414 | 213911.1414 | 213911.1414 | 213911.1414 | 711138.61 | 1700593.5745 | 2411732.1845 | 38263.8255
Travel | #DIV/0! | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC | 6.16% | 624501 |  | 38466.48 | 49089.22 | 46136.6 | 46744.56 | 43004.8 | 49204.8 | 49204.8 | 49204.8 | 49204.8 | 49204.8 | 51704.8 | 133692.3 | 387478.16 | 521170.46 | 103330.54
Subtotal Direct costs Milestone 59 |  | 3074497.01 | 0 | 354868.86 | 316056.32 | 173905.73 | 249960.1444 | 256915.9414 | 263115.9414 | 263115.9414 | 263115.9414 | 263115.9414 | 263115.9414 | 265615.9414 | 844830.91 | 2088071.7345 | 2932902.6445 | 141594.3655
Indirect Costs - Milestone 59 |  | 1544456.22 |  | 221353.1 | 172675.67 | 92287.78 | 134266.3174 | 139937.9656 | 141332.9656 | 141332.9656 | 141332.9656 | 141332.9656 | 141332.9656 | 141895.4656 | 486316.55 | 1122764.5768 | 1609081.1268 | -64624.9068
Fee costs Milestone 59 |  | 230947.6615 | 0 | 28811.098 | 24436.5995 | 13309.6755 | 20222.4454 | 19842.6954 | 20222.4454 | 20222.4454 | 20222.4454 | 20222.4454 | 20222.4454 | 20375.5704 | 66557.373 | 161552.9378 | 228110.3108 | 2837.3507
Total Milestone 59 | 12.48% | 4849897.8915 | 0 | 605033.058 | 513168.5895 | 279503.1855 | 404448.9071 | 416696.6024 | 424671.3524 | 424671.3524 | 424671.3524 | 424671.3524 | 424671.3524 | 427886.9774 | 1397704.833 | 3372389.2492 | 4770094.0822 | 79806.8093
Total Award | 55.12% | 33707478.4095 | 0 | 11787301.554 | 2692098.1945 | 4099160.976 | 2629214.6742 | 2384619.0209 | 2534941.6179 | 2574573.8686 | 3028015.837 | 612057.5503 | 594751.7043 | 771229.5816 | 18578560.7245 | 15129403.8549 | 33707964.5794 | -486.1699